## WO with Payment Term Draft
EBD - NORTHERN REGION | [8 empty] | Intent of Form: DRAFT: shared with Contractor to review and agree to take on the job FINAL: Agreed upon and signed scope of work between AEA and Contractor
PROJECT WORK ORDER | [5 empty] | PROJECT TYPE: | Single Family
Version 2
PROJECT INFORMATION | [5 empty] | CONTRACTOR INFORMATION
Project Name: |  | Villa Apartments |  |  |  | Contractor Name: |  | ABC Construction
Property Address: |  | 123 Villa Street |  |  |  | Address: |  | 111 A Street, San Francisco, CA 94110
City / State / Zip: |  | San Francisco / CA / 90014 |  |  |  | Phone: |  | (098) 765-4321
Owner / Owner's Representative: |  | John Smith |  |  |  | Email: |  | abc-construction@gmail.com
Owner Contact Information: |  | (123) 456-7890
No. of Units: |  | 25 |  |  |  | Status
No. of Buildings: |  | 1 |  |  |  | Draft
Year Built: |  | 1970 |  |  |  | Final |  |  |  |  | Single Family
Multifamily
PROPOSED SCOPE OF WORK MEASURES | [10 empty] | M&MH
Enter each retrofit measure below. All cost caps represent maximum allowable reimbursement per measure.
# | Proposed Measure |  | Qty | Difficulty | Labor Cap | Equipment Cap | Total Measure Cap | Measure Description |  | Additional Measure Scope Description
1 | Unitary Tank Type HPWH |  | 1 | Standard | 2320 | 5000 | 7320 | Position unit for accessible controls Minor modifications to accommodate tank (e.g. enlarge platform in garage) Assumes install location meets manufacturer requirements without venting intervention (e.g.: ducting, louvers) Connect to existing water, T&P, and drain pan lines Install drain pan and connect to appropriate discharge Insulate accessible hot water pipes Install seismic straps Run new condensate discharge line (adjacent indirect laundry standpipe, landscape, etc.) Install thermostatic mixing valve Connect to existing circuit (e.g. 120v plug in model) Program water heater for TOU optimization Test |  | Comply with relevant requirements in EBD Measure Installation and Performance Requirements. 65 gallon , 240 V HPWH
1a | General - Patch, Prime, & Paint |  | 1 | Standard | 87 | 0 | 87
2 | Induction Range |  | 25 | Moderate | 15395.7 | 75000 | 90395.7 | Disconnect and cap gas line Remove and dispose of old range Install new range on existing 240v circuit Instruct occupant on operation and cookware Run new 240v circuit or other defined electrical infrastructure to support new range including outlet/receptacle and breaker - new circuit meets definition of moderate May require minor patching for new electrical. Circuit isassumed as a moderate installation. Drywall repair, mudding and priming is an associated stand-alone measure and cost. Provide pots and pans |  | Comply with relevant requirements in EBD Measure Installation and Performance Requirements.
3 | [6 empty] | 0
4 | [6 empty] | 0
5 | [6 empty] | 0
6 | [6 empty] | 0
7 | [6 empty] | 0
8 | [6 empty] | 0
9 | [6 empty] | 0
SUBTOTAL |  |  |  |  | 17802.7 | 80000 | 97802.7
# | Project Level Costs |  | Qty |  | Labor Cap |  | Total | Notes
1 | Assessment |  |  |  | 1 | n/a | 1
2 | Engineering |  |  |  | 2 | n/a | 2
3 | HERS |  |  |  | 3 | n/a | 3
4 | Permits |  |  |  | 4 | n/a | 4
5 | Project close out |  |  |  | 5 | n/a | 5
6 | Other |  |  |  | 0 | n/a | 0
PROJECT LEVEL COSTS |  |  |  |  | 15
TOTAL PROJECT COST CAP |  |  |  |  | 97817.7
For details and requirements for each Proposed Measure, see Minimum Project Requirements in [Project Folder].
For payment terms and process, see Master Agreement in [Contractor Folder].
A Work Order Revision Request can be submitted at the link below to request changes to the measure cost caps. Any Work Order Revision Request must include detailed, written justification for requested measure difficulty changes. Supporting documentation (photos, schematics, etc.) may be provided and/or requested. Any measure exceeding its cost cap requires written authorization from the Program Administrator prior to work commencing. [Work Order Revision Request Link]
Invoices can be submitted in a maximum of 4 installaments as defined below. Multiple installments can be included in one invoice.
Payment Terms |  | Required Documentation Submitted with Invoice |  |  |  | % of Project Cost | Invoice Amount
Installment 1: Equipment order |  | Purchase order for all major equipment that is being installed (e.g. ranges, water heaters, HVAC) Construction schedule |  |  |  | 10% | 9781.77
Installment 2: Commence Work |  | Work on site has commenced and 25% completion of construction schedule. Submission of construction schedule submitted. |  |  |  | 25% | 24454.425
Installment 3: Completion of Work |  | All installation work has been completed and final documentation has been submitted to Program |  |  |  | 55% | 53799.735
Installment 4: Permit Finaled |  | Copy/ Photo of permit signed of by AHJ |  |  |  | 10% | 9781.77
INSPECTION & QUALITY CONTROL
Program Administrator will review submittals prior to construction and inspect each measure during and after installation. Any measure found to not meet program requirements shall be corrected prior to payment.
AUTHORIZATION & SIGNATURES
By signing below, all parties confirm they have reviewed this Work Order and agree to its terms.
Contractor |  |  |  |  | Program Administrator
Date: |  |  |  |  | Date: